Project Timeline Chart for "DrawMotion" (4 Months)

| Phase | Task | Duration | Start Date | End Date | Responsible |
| --- | --- | --- | --- | --- | --- |
| 1. Project Planning | Define project scope and objectives | 1 week | Month 1, Week 1 | Month 1, Week 1 | All |
|  | Requirement gathering (interviews, surveys) | 1 week | Month 1, Week 1 | Month 1, Week 2 | All |
|  | Literature review and research | 1 week | Month 1, Week 1 | Month 1, Week 2 | All |
|  | Finalize project plan and timeline | 1 week | Month 1, Week 2 | Month 1, Week 3 | All |
| 2. Algorithm Development | Design hand detection algorithm | 2 weeks | Month 1, Week 3 | Month 2, Week 1 | Shlok Goswami |
|  | Implement hand tracking algorithm | 2 weeks | Month 2, Week 1 | Month 2, Week 3 | Shlok Goswami |
|  | Develop gesture recognition algorithm | 2 weeks | Month 2, Week 3 | Month 3, Week 1 | Shlok Goswami |
|  | Test and optimize algorithms | 1 week | Month 3, Week 1 | Month 3, Week 2 | Shlok Goswami |
| 3. Application Development | Integrate algorithms with application framework | 2 weeks | Month 3, Week 2 | Month 3, Week 4 | Akshay Gojiya |
|  | Develop drawing module (canvas, tools) | 2 weeks | Month 3, Week 4 | Month 4, Week 1 | Akshay Gojiya |
|  | Implement UI/UX features | 2 weeks | Month 4, Week 1 | Month 4, Week 3 | Sai Mistry |
|  | Optimize application performance | 1 week | Month 4, Week 3 | Month 4, Week 4 | Akshay Gojiya |
| 4. User Testing | Conduct usability testing with users | 1 week | Month 4, Week 4 | Month 4, Week 4 | All |
|  | Gather feedback and make necessary adjustments | 1 week | Month 4, Week 4 | Month 4, Week 4 | All |
| 5. Finalization | Finalize documentation and user manuals | 1 week | Month 4, Week 4 | Month 4, Week 4 | Sai Mistry |
|  | Prepare for project presentation | 1 week | Month 4, Week 4 | Month 4, Week 4 | All |
|  | Project presentation and feedback | 1 week | Month 4, Week 4 | Month 4, Week 4 | All |